## Sheet1
MyBrus 04/01/2015 - 08/01/2015
Task Name | Description | Start Date | Estimate | EndDate | Status | Explaination
Design database | Converts all requests to database and create ERP diagram | 2015-03-30 | 25 hours | 2015-04-03 | Done | Need confirm
Architect application | Architect application and hook it up with database | 2015-04-04 | 40 hours | 2015-04-14 | Working
Create application UI | Hookup ui, frontend with backend | 2015-04-14 | 50 hours | 2015-04-25
Godday testing | Deploy application to domain mybrus.com on Godday for testing | 2015-04-25 | 20 hours | 2015-05-01
Dashboard template | UI for administator modify application | 2015-05-01 | 40 hours | 2015-05-11
User management | Login, logout, etc | 2015-05-11 | 20 hours | 2015-05-16
Main page | Main page for customer look up brushes | 2015-05-18 | 40 hours | 2015-05-25
Cart Mangement | Add, edit, delete cart | 2015-05-26 | 40 hours | 2015-06-03
Credit Card Module | Credit card transaction process | 2015-06-04 | 75 hours | 2015-06-20
Testing Transaction | Hookup module to domain, and testing | 2015-06-22 | 40 hours | 2015-06-30
Sale Report | Show sale report and submit shipping status | 2015-07-01 | 20 hours | 2015-07-06
Product Management | Add, edit, delete brushes information | 2015-07-07 | 40 hours | 2015-07-15
Final testing | Final testing before deploye to production | 2015-07-16 | 40 hours | 2015-07-25
Estimate spending 5 hours/days
Note on L3: Admin: Click to see more detail

## Sheet2
Application Requests
Brush (Co) | Customer | About | Privacy Policy
Image | Phone
Color? | Email
Size? | Addess
Name?
Something else
Note on A1: Admin: You just tell me more details about what information you are going to store in your application. For example, on brush, you want to keep like image, color, and something else??